## Initial Gantt Chart
AM Project Gantt Chart |  | 2020-03-02 |  |  | 2020-03-09 |  |  | 2020-03-16 |  |  | 2020-03-23 |  |  | 2020-03-30 |  |  | 2020-04-06 |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  | 2020-05-04
Assigned Members | Task | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F
Everyone | Task: Design Topic Decision
Dahlia, Erick | Task: Customer Needs Analysis
Erick, Chris | Task: Market Analysis (Part cost)
Chris, Ryan | Task: Mechanical Analysis
Everyone | Task: Set Design Constraints
Dahlia, Erick | Task: Create Specification Sheet
Ryan | Task: CAD model draft
Everyone | Task: Project Proposal (Due 3/25)
Everyone | Task: Product Choice
Erick, Chris, Ryan | Task: Tolerance & Safety Analysis
Ryan, Chris | Task: Complete CAD model
Ryan | Task: Create STL files (Due 4/12)
N/A | Task: Print parts
Everyone | Task: Assemble and post processing
Everyone | Task: Part Evaluation
Dahlia | Task: Customer Survey
Everyone | Task: Final Presentation (May 5,7)
Everyone | Task: Final Report (5/8)

## After Proposal
AM Project Gantt Chart |  | 2020-04-06 |  |  | 2020-04-13 |  |  | 2020-04-20 |  |  | 2020-04-27 |  |  | 2020-05-04
Assigned Members | Task | M | W | F | M | W | F | M | W | F | M | W | F | M | W | F
Everyone | Task: Design Topic Decision
Dahlia, Erick | Task: Customer Needs Analysis
Erick, Chris | Task: Market Analysis (Part cost)
Everyone | Task: Product Choice
Everyone | Task: Set Design Constraints
Dahlia, Erick | Task: Create Specification Sheet
Ryan | Task: CAD model draft
Everyone | Task: Project Proposal (Due 4/6)
Chris, Ryan | Task: Mechanical Analysis
Erick, Chris, Ryan | Task: Tolerance & Safety Analysis
Ryan, Chris | Task: Complete CAD model
Ryan | Task: Create STL files (Due 4/30)
N/A | Task: Print parts (?)
Everyone | Task: Assemble and post processing
Everyone | Task: Part Evaluation
Dahlia | Task: Customer Survey
Everyone | Task: Final Presentation (May 5,7)
Everyone | Task: Final Report (5/8)